2018 THIRD QUARTER BUDGET APPRAISAL

BY

MONITORING & EVALUATION DEPARTMENT,

MINISTRY OF ECONOMIC PLANNING & BUDGET

October, 2018

TABLE OF CONTENTS

Title Page…………………………….........................................................1

Table of Contents…………………………………………………………………………2

List of Tables……………….………………………………………………………………3

List of Figures………………………………………………………………………………5

Preface………………………………………………………………………..................8

Executive Summary………………………………………………………………………9

Chapter One:	Introduction………………………………………………………12

Chapter Two: 	Revenue Profile and Analysis……………………………...15

Chapter Three: 	Expenditure Profile and Analysis………………………....27

Chapter Four: 	Status of Capital Projects Awarded between

January and September, 2018………………..…………..66

Chapter Five: 	Observations, Recommendations and Conclusions..73

Appendix..………………………………………………………………………………….77

LIST OF TABLES

Table 2.1: Summary of Revenue Receipts (July - September, 2018)..15

Tabl2 2.2: Summary of Quarterly Revenue receipts, 2018………………16

Table 2.3: Details of Quarterly Revenue Receipts from Federation

Account…………………………………………………………..………..22

Table 2.4: Details of Quarterly Independent Revenue…………….………24

Table 2.5: Details of Quarterly Revenue Receipts from

Other Revenue Sources…………………………………………..….25

Table 3.1: Summary of 2018 Third Quarter Expenditure……….………..27

Table 3.2: Summary of 2018 Quarterly Expenditures………………………29

Table 3.3: Details of Quarterly Recurrent Expenditure Components….35

Table 3.4: Details of Quarterly Personnel Cost……….….…………………..40

Table 3.5: Summary of Quarterly Subvention/Grants to Parastatals….46

Table 3.6: Details of Quarterly Consolidated Revenue

Funds Charges (CRFC)………………………………………………….50

Table 3.7: Quarterly Sectoral Recurrent Expenditure Details..……….…56

Table 3.8: Details of Quarterly Statutory Transfers...………………………60

Table 3.9:  Quarterly Sectoral Capital Expenditure Details….……………62

Table 4.1: Summary of Projects Awarded from January- Sept., 2018.67

Table 4.2: Classification of the UBEC/SUBEB 599 Projects……………….70

Table 4.3: Number of projects with the level of Work Done

on SUBEB Projects……………………………………………………..72

Table 4.4: Classifications of Projects into LGAs………………………………74

Table 4.5: Number of projects with the level of Work Done

by OSOPADEC………….……………………………………………..75

Table 4.6: Number of projects with the level of Work Done

by Minstry of Works and Infrastructure….…………………..76

LIST OF FIGURES

Figure 2.1: Bar Chart Showing Quarterly Revenue Performance.……16

Figure 2.2: Bar Chart Showing Quarterly Performance of

Revenue Categories …………………………………………………18

Figure 2.3: Pie Chart Showing Share of Third Quarter

Actual Revenue Components……………………………………..20

Figure 2.4: Bar Chart Showing Quarterly Performance of

Revenue Receipts from Federation Account…………………23

Figure 2.5: Bar Chart Showing Quarterly Independent

Revenue Performance..………………….……………………….25

Figure 2.6: Bar Chart Showing Quarterly Performance of Revenue

Receipts from Other Revenue Sources……………………..26

Figure 3.1: Bar Chart Showing Quarterly Total Expenditure

Performance……………………………………………………………28

Figure 3.2: Bar Chart Showing Quarterly Performance of

Expenditure Classifications………………………………………..31

Figure 3.3: Pie Chart Showing Share of Third Quarter Actual

Expenditure Performance………………………………………….33

Figure 3.4: Bar Chart Showing Quarterly Recurrent Expenditure

Components…………………………………………………………….36

Figure 3.5: Pie Chart Showing Share of Third Quarter Actual

Recurrent Expenditure Components…………….…………….38

Figure 3.6: Bar Chart Showing Quarterly Personnel Cost………………40

Figure 3.7: Pie Chart Showing Share of Third Quarter

Personnel Cost Details………..…………………………………..41

Figure 3.8: Bar Chart Showing Quarterly Overhead Cost………………42

Figure 3.9: Bar Chart Showing Quarterly Special Programme.………44

Figure 3.10: Bar Chart Showing Quarterly Subventions to

Institutions and Agencies……………………………………….47

Figure 3.11: Bar Chart Showing Quarterly Consolidated

Revenue Fund Charges (CRFC)………………………………51

Figure 3.12: Bar Chart Showing Quarterly Grants/Loan……………….53

Figure 3.13: Bar Chart Showing Quarterly Sectoral

Recurrent Expenditure……………………………….………….57

Figure 3.14: Bar Chart Showing Quarterly Statutory Transfer………60

Figure 3.15: Bar Chart Showing Quarterly Sectoral

Capital Expenditure…………………………………..…………..63

Figure 4.1: Bar Chart Showing Number of Projects

With the Level of Work Done on SUBEB Projects.………67

Figure 4.2: Bar Chart Showing Number of OSOPADEC Projects

With the Level of Work Done…………………………..………70

PREFACE

Budget is an estimate of costs, revenues, and resources over a specified period, reflecting a reading of future financial conditions and goals. It is compiled and re-evaluated on a periodic basis; hence, budget performance report is an essential part of the State accountability mechanism stipulated in the Ondo State Fiscal Responsibility Law, 2017.

The year 2018 budget was the second budget prepared under the Arakunrin Oluwarotimi Odunayo Akeredolu-led Administration to implement his five cardinal Programmes for the development of Ondo State.

This Appraisal, therefore, evaluates the implementation of the 2018 Third Quarter estimates with respect to all disbursements and assesses the realisation of all fiscal targets during the periods under review. Also, it identifies gaps, provides lessons, highlights significant accomplishments, and offers recommendations for improvement.

The publication of this report is principally in fulfillment of Section 39(3) of the Ondo State Fiscal Responsibility Law, (FRL), 2017. We therefore, urge the general public and readers of this Report to maintain active interest in tracking progress towards attainment of Government’s goals and objectives especially government’s management of public resources. We look forward to your active participation in the entire budget process.

Department of Monitoring and Evaluation,

Ministry of Economic Planning and Budget,

Alagbaka, Akure.

EXECUTIVE SUMMARY

The 2018 Budget has the theme “Budget of Progress” and is closely linked to the Strategic Development and Policy Implementation plan document tagged the Blueprint to Progress of this administration. The Budget was therefore designed to demonstrate Government’s commitment to create a more diversified, sustainable and inclusive economy. It has the objective to open up the hidden potentials of our people, communities and natural endowments across every part of the State.

The State approved a total budget of N181.425 billion in 2018. The budget is broken into N13.600 billion for Debt Repayment (Principal), N8.308 billion for Statutory Transfers, N78.588 billion for Recurrent Expenditure and N80.929 billion for Capital Expenditure, with a corresponding total of N181.425 billion as envisaged revenue for the year.

The revenue side of the budget for the third quarter of the year 2018 recorded total receipts of N26.945 billion against proposed target of N45.356 billion for the period. The breakdown of these receipts for the third quarter showed Internally Generated Revenue (IGR) as N4.122 billion, N18.167 billion as revenue from the Federation Account and N4.656 Billion as revenue from Other sources. These figures depicted that revenue performance level was 59.4% for the third quarter of the fiscal year.

On the other hand, the total actual expenditure for the third quarter was N26.117 billion against the proposed estimates of N45.356 billion. This figure depicted overall performance level of 57.6% for the period. The breakdown of the figures for the Third Quarter showed that the actual recurrent expenditure was N19.146 billion, representing 97.4%, Debt Repayment N1.544 billion, representing 45.4%, Statutory Transfer N1.625 billion, representing 78.2%, while the actual capital expenditure stood at N3.803 billion, representing 18.8% performance.

Further breakdown and analysis of the appraisal is structured in chapters. Chapter one discusses the introduction, objectives and policy thrust of the 2018 budget. Details of revenue profile and analysis for the third quarter are contained in chapter two. Chapter three focuses on the expenditure profile and analysis, Chapter four covers Status of capital projects awarded between January and September 2018 while chapter five highlights the observations, recommendations and conclusion.

CHAPTER ONE

1.1	INTRODUCTION

1.2	BACKGROUND

The 2018 Budget was closely linked with the Strategic Development and Policy Implementation Plan document tagged the Blueprint to Progress of this administration and was designed to focus on rebuilding the State’s economy through prioritised investment on infrastructural facilities and agriculture-related activities. It also aimed at strengthening partnership between public and private sector as well as Development Partners to leverage and catalyze resources for growth.

The 2018 Third-Quarter Budget Appraisal Report  provides insight into the Ondo State Government’s Budget Implementation and Performance so far. It includes an overview of budget implementation activities, a brief analysis of the macroeconomic context within which the 2018 Budget was executed, and an analysis of the Government’s revenue receipts and expenditure in the third quarter.

Additionally, the report measures budget performance against the strategic goals, pillars and intended outcomes stipulated by the 2018 Appropriation Act and the Strategic Implementation Plan.

1.3	OBJECTIVES AND POLICY THRUST OF 2018 BUDGET

The 2018 Budget is hinged on the following objectives:

- Intensify efforts on Independent Revenue (IR) initiatives by increasing IR by 100%;

- Massive infrastructural development;

- Wealth creation through empowerment of youths, artisans, farmers and market women;

- Enhancement of agriculture related activities; and

- Enhancement of community development through improved collaboration with communities.

1.4	STRATEGIES FOR ACHIEVING OBJECTIVES OF 2018 	BUDGET

The Strategies to achieve the objectives of the 2018 Budget among others are:

- Activation of IPSAS revenue codes for easy lodgement of revenue;

- Engagement of Revenue Consultants to help drive Independent Revenue Generation;

- Resuscitation of decaying infrastructural facilities;

- Provision of farm inputs and improved seedlings to farmers to boost food production;

- Deployment of ICT to empower and create wealth for the youths and artisans;

- Collaboration with relevant Federal Agencies and Development partners to support State initiatives; and

- Enhancing accessibility to semi-urban and rural areas through opening-up of rural feeder roads.

1.5	METHODOLOGY

The Methodology adopted in the production of this report draws from a number of interrelated approaches. The aim is to offer representative information that accurately provides necessary context for verifying the quality, efficiency and effectiveness of the Government’s programmes and their attendant progress towards implementation, to reflect the increased demand for transparency and accountability in Government. A combination of desk review and data collection and analysis were adopted in order to justify budgetary resource allocation. Data were collected through the administration of uniform templates that were consistent with the M&E Framework. These primary levels data were collected from the MEDAs for further data quality, assessment, analysis and interpretation.

1.6	LIMITATIONS

Few limitations were encountered during the preparation of the report that may have affected timely reporting, quality and assumptions made in the report. These include:

- Inadequate MEDAs Compliance - Usually, several MEDAs found it difficult to meet the deadline to which they were expected to submit their returns. This hereby prolonged unneccessarily the stipulated time the report should be ready.

- Validation of Data – At times, when returns are rendered by MEDAs, there are contractions in the data with relevant Government institutions, so the Department tried to verify the data from MoF, BIR, AG, and DMD for quality basis.

- Untimely Release of Fund – Prompt release of fund for this exercise goes a long way to determine whether the exerecise will be completed as at when due.

CHAPTER TWO

2.1	REVENUE PROFILE AND ANALYSIS

The table below shows the details of the Revenue inflow to the State for the third quarter of the fiscal year 2018.

Table 2.1: Summary of Revenue Receipts (July – September,2018)

|  | Revenue Sources | Approved Budget (N’B) | Third Quarter Target (N’B) | Third Quarter Actual (N’B) | Performance (%) |
| --- | --- | --- | --- | --- | --- |
| (A) | Revenue from Federation Account |  |  |  |  |
| i. | Statutory Allocation | 25.352 | 6.338 | 10.265 | 161.96 |
| ii. | Value Added Tax | 12.000 | 3.000 | 2.960 | 98.67 |
| iii. | Mineral Derivation Fund | 15.536 | 3.884 | 4.167 | 107.29 |
| iv. | Budget Support Facility Loan | 10.925 | 2.731 | 0.000 | 0.00 |
| v. | Paris Club Refund | 13.156 | 3.289 | 0.000 | 0.00 |
| vi. | Petroleum Profit Tax/Excess Crude | 3.683 | 0.920 | 0.125 | 13.59 |
| vii. | Refund on Federal Roads | 10.000 | 2.500 | 0.000 | 0.00 |
| viii. | Exchange Gain/Forex Stabilization Account | 6.126 | 1.532 | 0.650 | 42.43 |
|  | Sub-total | 96.778 | 24.194 | 18.167 | 75.09 |
| (B) | Independent Revenue |  |  |  |  |
| i. | BIR | 13.652 | 3.413 | 2.617 | 76.68 |
| ii. | MEDAs | 7.276 | 1.842 | 1.505 | 81.71 |
| iii. | Revenue Retaining Agencies (RRA) |  | 0.000 | 0.923 | 0.00 |
|  | Sub-total | 20.928 | 5.255 | 5.045 | 96.00 |
| (C) | Other Revenue Sources |  |  |  |  |
| i. | Rollover Fund | 13.500 | 3.375 | 3.375 | 100.00 |
| ii. | Credit from Development Partners | 12.748 | 3.187 | 0.331 | 10.39 |
| iii. | Grants from donor agencies | 6.279 | 1.569 | 0.000 | 0.00 |
| iv. | Loans/Leases | 31.195 | 7.798 | 0.000 | 0.00 |
| v. | Excess Bank Charges |  | 0.000 | 0.000 | 0.00 |
| vi. | Fixed Deposit Recalls |  | 0.000 | 0.950 | 0.000 |
|  | Sub-total | 63.722 | 15.929 | 4.656 | 29.23 |
|  | Total | 181.428 | 45.378 | 27.868 | 61.41 |
|  | Less (RRA) |  |  | 0.923 |  |
|  | GRAND TOTAL | 181.428 | 45.378 | 26.945 | 59.38 |

Source: Office of Accountant General and Board of Internal Revenue, Ondo State

Table 2.2:	Summary of Quarterly Revenue Receipts, 2018

|  | Revenue Sources | Quarterly Targets (N’B) | First Quarter Actual (N’B) | Second Quarter Actual (N’B) | Third Quarter Actual (N’B) |
| --- | --- | --- | --- | --- | --- |
| (A) | Revenue from Federation Account |  |  |  |  |
| i. | Statutory Allocation | 6.338 | 9.444 | 9.556 | 10.265 |
| ii. | Value Added Tax | 3.000 | 2.819 | 2.757 | 2.960 |
| iii. | Mineral Derivation Fund | 3.884 | 4.874 | 4.418 | 4.167 |
| iv. | Budget Support Facility Loan | 2.731 | 0.004 | 0.000 | 0.000 |
| v. | Paris Club Refund | 3.289 | 0.000 | 0.000 | 0.000 |
| vi. | Petroleum Profit Tax/Excess Crude | 0.920 | 0.000 | 0.108 | 0.125 |
| vii. | Refund on Federal Roads | 2.500 | 0.000 | 0.000 | 0.000 |
| viii. | Exchange Gain/Forex Stabilization Account | 1.532 | 0.324 | 0.639 | 0.650 |
|  | Sub-total | 24.194 | 17.465 | 17.478 | 18.167 |
| (B) | Independent Revenue |  |  |  |  |
| i. | BIR | 3.413 | 2.420 | 2.882 | 2.617 |
| ii. | MEDAs | 1.842 | 1.190 | 0.757 | 1.505 |
| iii. | Revenue Retaining Agencies (RRA) | 0.000 | 0.557 | 2.114 | 0.923 |
|  | Sub-total | 5.255 | 4.167 | 5.753 | 5.045 |
| (C) | Other Revenues Sources |  |  |  |  |
| i. | Rollover Fund | 3.375 | 3.375 | 3.375 | 3.375 |
| ii. | Credit from Development Partners | 3.187 | 0.080 | 0.000 | 0.331 |
| iii. | Grants from donor agencies | 1.569 | 0.000 | 0.000 | 0.000 |
| iv. | Loans/Leases | 7.798 | 0.000 | 0.000 | 0.000 |
| v. | Excess Bank Charges | 0.000 | 0.004 | 0.004 | 0.000 |
| vi. | Fixed Deposit Recalls | 0.000 | 0.000 | 0.000 | 0.950 |
|  | Sub-total | 15.929 | 3.459 | 3.379 | 4.656 |
|  | Total | 45.378 | 25.091 | 26.610 | 27.868 |
|  | Less (RRA) |  | 0.557 | 2.114 | 0.923 |
|  | GRAND TOTAL | 45.378 | 24.534 | 24.496 | 26.945 |

Source: Office of Accountant General and Board of Internal Revenue, Ondo State

Table 2.2 above classifies the revenue receipts to the State into three categories. These are: Revenue from the Federation Account, Independent Revenue (Internally Generated Revenue, IGR) and Revenue from Other Sources. It also shows the total revenue generated from these categories in the first, second and third quarters of 2018.

Figure 2.1: Bar Chart Showing Quarterly Revenue Performance

Figure 2.1 above compares the total actual revenue for the first, second and third quarters with the proposed quarter revenue target. It showed that the actual total revenue for the three quarters were N24.534 billion, N24.496 billion and N26.945 billion respectively against the proposed quarterly revenue targets of N45.378 billion, representing 54.07%, 53.98% and 59.38% performance level. However, when the actual revenue generated by the Revenue Retaining Agencies (RRA) were added to these figures, it indicated a moderate increase to N25.091 billion, N26.610 billion, N27.868 billion for the three quarters.

Figure 2.2: Bar Chart Showing Quarterly Performance of Revenue  Categories

Figure 2.2 above depicted further analysis of the revenue performance of the three categories of the revenue sources to the State. Comparing each revenue class targets with the actual recorded for the first, second and third quarters. The quarterly revenue targets from the Federation Account was N24.194 billion. At the end of the quarter, actual revenue for the first quarter from this category was N17.465 billion, Second quarter N17.478 billion and Third quarter  N18.167 billion, representing 72.19%, 72.24% and 75.09% levels of performance respectively. In similar manner, a target of N5.255 billion was set for Independent Revenue for each quarter of year 2018 while the actual revenue generated for the first quarter was N3.610 billion, Second quarter N3.639 billion and Third quarter N4.122 billion, with performance levels of 68.70%, 69.25% and 78.44% respectively. Revenue generated by Revenue Retaining Agencies (RRA) for three quarters were not added to these figures. Following the same trend, revenue targets from Other Sources recorded actuals of N3.459 billion, N3.379 billion and N4.656 billion respectively for the three quarters, against the proposed revenue targets of N15.929, thus performing at 21.72%, 21.21% and 29.23% levels.

Figure 2.3: Pie Chart Showing Share of Third Quarter Actual 				  Revenue

Figure 2.3 above displays the comparative share of actual revenue receipts from the three revenue source classifications for the third quarter of year 2018. Out of the total actual receipts of N26.945 billion for the quarter, the receipts for Independent Revenue accounted for 15%, Revenue from Other Sources 17% while revenue receipts from the Federation Account accounted for the largest share of 68% of the total receipts by the State for the quarter.

Table 2.3: Details of Quarterly Revenue Receipts from Federation Account

|  | Revenue Sources | Quarterly Targets (N’B) | First Quarter Actual (N’B) | Second Quarter Actual (N’B) | Third Quarter Actual (N’B) |
| --- | --- | --- | --- | --- | --- |
| (A) | Revenue from Federation Account |  |  |  |  |
| i. | Statutory Allocation | 6.338 | 9.444 | 9.556 | 10.265 |
| ii. | Value Added Tax | 3.000 | 2.819 | 2.757 | 2.960 |
| iii. | Mineral Derivation Fund | 3.884 | 4.874 | 4.418 | 4.167 |
| iv. | Budget Support Facility Loan | 2.731 | 0.004 | 0.000 | 0.000 |
| v. | Paris Club Refund | 3.289 | 0.000 | 0.000 | 0.000 |
| vi. | Petroleum Profit Tax/Excess Crude | 0.920 | 0.000 | 0.108 | 0.125 |
| vii. | Refund on Federal Roads | 2.500 | 0.000 | 0.000 | 0.000 |
| viii. | Exchange Gain/Forex Stabilization Account | 1.532 | 0.324 | 0.639 | 0.650 |
|  | Total | 24.194 | 17.465 | 17.478 | 18.167 |

Source: Ondo State Office of the Accountant-General

Figure 2.4: Bar Chart Showing Quarterly Performance of Revenue Receipts from Federation Account

Figure 2.4 above depicts the performance of revenue heads from the Federation Account and quarterly comparison of the various heads for the first, second and third quarters of the year 2018. The quarter targets of the revenue heads were compared with the respective quarter actuals. The quarter revenue targets for Statutory Allocation was N6.338 billion, Value Added Tax was N3.000, Mineral Derivation Fund N3.884 billion, Budget Support Facility Loan N2.731 billion, Paris Club Refund N3.289 billion, Petroleum Profit Tax/Excess Crude N0.920 billion, Refunds on Federal Roads N2.500 billion and Exchange Gain/Forex Stabilization Account N1.532 billion.

Data from the Office of the Accountant General revealed that revenues were not received for Paris Club Refund and Refund on Federal Roads in the three quarters while a breakdown of the receipts from the Federation Account further showed that the actuals of Statutory Allocation was N10.265 billion, Value Added Tax N2.960 billion, Mineral Derivation Fund N4.167 billion, Petroleum Profit Tax/Excess Crude N0.125 billion and Exchange gain/Forex Stabilization Account N0.650 billion, in the same order, representing 161.96%, 98.67%, 107.29%, 13.59% and 42.43% performance levels respectively for third quarter. Budget Support Facility Loan only recorded a receipt of N0.004 billion in the first quarter.

Table 2.4:	Details of Quarterly Independent Revenue

|  | Revenue Source | Quarterly Targets (N’B) | First Quarter Actual (N’B) | Second Quarter Actual (N’B) | Third Quarter Actual (N’B) |
| --- | --- | --- | --- | --- | --- |
| (B) | Independent Revenue |  |  |  |  |
|  | BIR | 3.413 | 2.420 | 2.882 | 2.617 |
|  | MEDAs | 1.842 | 1.190 | 0.757 | 1.505 |
|  | Revenue Retaining Agencies (RRA) | 0.000 | 0.557 | 2.114 | 0.923 |
|  | TOTAL | 5.255 | 4.167 | 5.753 | 5.045 |
|  | TOTAL (Less RRA) |  | 3.610 | 3.639 | 4.122 |

Source: Board of Internal Revenue

Figure 2.5 below depicts the comparison between the quarter target for Internally Generated Revenue (IGR) with the actual revenue in the first, second and third quarters. The IGR quarter target for 2018 was N5.255 billion while the total actual IGR reported by the Board of Internal Revenue for the first quarter was N3.610 billion, the second quarter revenue was N3.639 billion while the third quarter revenue generated was N4.122 billion. (These totals do not include RRA figures) representing 68.70%, 69.25% and 78.44% performance level respectively.

Figure 2.5: Bar Chart Showing Quarterly Independent Revenue  	  		  performance

Table 2.5: Details of Quarterly Revenue receipts from Other Revenue Sources

|  | Revenue Source | Quarterly Targets (N’B) | First Quarter Actual (N’B) | Second Quarter Actual (N’B) | Third Quarter Actual (N’B) |
| --- | --- | --- | --- | --- | --- |
| (C) | Other Revenues: |  |  |  |  |
| i. | Rollover Fund | 3.375 | 3.375 | 3.375 | 3.375 |
| ii. | Credit from Development Partners | 3.187 | 0.080 | 0.000 | 0.331 |
| iii. | Grants from Donor Agencies | 1.569 | 0.000 | 0.000 | 0.000 |
| iv. | Loans/Leases | 7.798 | 0.000 | 0.000 | 0.000 |
| v. | Excess Bank Charges | 0.000 | 0.004 | 0.004 | 0.000 |
| vi. | Fixed Deposits Recalls | 0.000 | 0.000 | 0.000 | 0.950 |
|  | Total | 15.929 | 3.459 | 3.379 | 4.656 |

Source: Ondo State Office of the Accountant-General

Figure 2.6: Bar Chart Showing Performance of Revenue Receipts from Other Revenue Sources

Figure 2.6 above depicts the performance of revenue heads from Other Revenue sources for the first, second and third quarter of the year 2018. The quarterly targets of the revenue heads were compared with the respective quarter actuals. The quarter revenue targets for Roll Over Fund, Credit from Development Partners, Grants from Donor Agencies, and Loans/Leases were N3.375 billion, N3.187 billion, N1.569 billion, and N7.798 billion respectively.

Data from Ondo State Office of the Accountant-General revealed that there were no revenue receipts for Grants from Donor Agencies and Loans/Leases. The actual revenue receipt for Roll over fund were N3.375 billion in each quarter, Credit from Development Partners were N0.080 billion and N0.331 billion for the first and third quarter as there was no receipt for the second quarter. On Excess Bank Charges, the first and second quarter recorded N0.004 billion, there was no revenue receipt on this head in the third quarter. Fixed Deposit Recalls only recorded earnings in the third quarter, which is N0.950 billion. This further indicate that revenue receipts from Other Sources for the three quarters performed at 21.72%, 21.21%, 29.23% level of the quarterly target.

CHAPTER THREE

  - EXPENDITURE PROFILE AND ANALYSIS

The table below shows the details of the third quarter expenditure by the State for the year 2018.

Table 3.1: Summary of 2018 Third Quarter Expenditure

| S/N | EXPENDITURE DETAILS | APPROVED ESTIMATES (N) | THIRD QUARTER ESTIMATES (N) | THIRD QUARTER ACTUAL (N) | PERFORMANCE LEVEL (%) |
| --- | --- | --- | --- | --- | --- |
| 1 | PERSONNEL COST | 37,909,962,000.00 | 9,477,490,500.00 | 8,489,554,539.75 | 89.6 |
| 2 | OVERHEAD COST | 4,489,289,500.00 | 1,122,322,375.00 | 893,618,741.49 | 79.6 |
| 3 | SPECIAL PROGRAMME | 16,311,254,300.00 | 4,077,813,575.00 | 3,165,143,100.95 | 77.6 |
| 4 | GRANTS TO PARASTATALS/SUBVENTION | 7,227,169,686.07 | 1,806,792,421.52 | 2,458,784,584.00 | 136.1 |
| 5 | CONSOLIDATED REVENUE FUND CHARGE | 12,500,000,000.00 | 3,125,000,000.00 | 4,103,021,833.73 | 131.3 |
| 6 | GRANTS/LOANS | 150,000,000.00 | 37,500,000.00 | 35,465,600.00 | 94.6 |
| A | TOTAL RECURRENT EXPENDITURE | 78,587,675,486.07 | 19,646,918,871.52 | 19,145,588,399.92 | 97.4 |
|  | DEBT SERVICE | 13,599,878,084.63 | 3,399,969,521.16 | 1,543,500,745.67 | 45.4 |
| B | DEBT REPAYMENT (PRINCIPAL) | 13,599,878,084.63 | 3,399,969,521.16 | 1,543,500,745.67 | 45.4 |
|  | STATUTORY TRANSFERS |  |  |  |  |
| 1 | TRANSFER TO LOCAL GOVERNMENT JOINT ACCOUNT (10%) | 2,093,364,678.30 | 523,341,169.58 | 145,711,156.69 | 27.8 |
| 2 | TRANSFER TO OSOPADEC | 6,214,636,800.00 | 1,553,659,200.00 | 1,479,147,014.34 | 95.2 |
| C | TOTAL STATUTORY TRANSFER | 8,308,001,478.30 | 2,077,000,369.58 | 1,624,858,171.03 | 78.2 |
|  | CAPITAL EXPENDITURE |  |  |  |  |
| 1 | MEDAs/INSTITUTIONS | 80,928,985,234.00 | 20,232,246,308.50 | 3,803,443,519.34 | 18.8 |
| D | TOTAL CAPITAL EXPENDITURE | 80,928,985,234.00 | 20,232,246,308.50 | 3,803,443,519.34 | 18.8 |
|  | GRAND TOTAL (A+B+C+D) | 181,424,540,283.00 | 45,356,135,070.75 | 26,117,390,835.96 | 57.6 |

Source: Office of Accountant General and Debt Management Office, Ondo State

Table 3.2: Summary of 2018 Quarterly Expenditures

| S/N | EXPENDITURE DETAILS | QUARTERLY ESTIMATES (N) | FIRST QUARTER ACTUAL (N) | SECOND QUARTER ACTUAL (N) | THIRD QUARTER ACTUAL (N) |
| --- | --- | --- | --- | --- | --- |
| 1 | PERSONNEL COST | 9,477,490,500.00 | 7,922,604,467.29 | 8,629,192,940.34 | 8,489,554,539.75 |
| 2 | OVERHEAD COST | 1,122,322,375.00 | 781,682,376.65 | 1,001,709,911.30 | 893,618,741.49 |
| 3 | SPECIAL PROGRAMME | 4,077,813,575.00 | 2,035,929,337.84 | 2,200,655,856.46 | 3,165,143,100.95 |
| 4 | GRANTS TO PARASTATALS/SUBVENTION | 1,806,792,421.52 | 919,742,037.50 | 1,244,867,337.50 | 2,458,784,584.00 |
| 5 | CONSOLIDATED REVENUE FUND CHARGE | 3,125,000,000.00 | 3,735,999,309.07 | 3,592,314,385.46 | 4,103,021,833.73 |
| 6 | GRANTS/LOANS | 37,500,000.00 | 35,465,600.00 | 26,599,200.00 | 35,465,600.00 |
| A | TOTAL RECURRENT EXPENDITURE | 19,646,918,871.52 | 15,431,423,128.35 | 16,695,339,631.06 | 19,145,588,399.92 |
|  | DEBT SERVICE | 3,399,969,521.16 | 2,580,733,868.32 | 1,541,661,485.94 | 1,543,500,745.67 |
| B | DEBT REPAYMENT (PRINCIPAL) | 3,399,969,521.16 | 2,580,733,868.32 | 1,541,661,485.94 | 1,543,500,745.67 |
|  | STATUTORY TRANSFERS |  |  |  |  |
| 1 | TRANSFER TO LOCAL GOVERNMENT JOINT ACCOUNT (10%) | 523,341,169.58 | 127,868,122.86 | 133,982,328.17 | 145,711,156.69 |
| 2 | TRANSFER TO OSOPADEC | 1,553,659,200.00 | 639,125,944.35 | 1,721,554,600.17 | 1,479,147,014.34 |
| C | TOTAL STATUTORY TRANSFER | 2,077,000,369.58 | 766,994,067.21 | 1,855,536,928.34 | 1,624,858,171.03 |
|  | CAPITAL EXPENDITURE |  |  |  |  |
| 1 | MEDAs/INSTITUTIONS | 20,232,246,308.50 | 2,754,753,441.25 | 2,416,596,215.37 | 3,803,443,519.34 |
| D | TOTAL CAPITAL EXPENDITURE | 20,232,246,308.50 | 2,754,753,441.25 | 2,416,596,215.37 | 3,803,443,519.34 |
|  | GRAND TOTAL (A+B+C+D) | 45,356,135,070.75 | 21,533,904,505.13 | 22,509,134,260.71 | 26,117,390,835.96 |

Source: Office of Accountant General and Debt Management Office, Ondo State

Table 3.2 above shows the details of the quarterly expenditures by the State for the First, Second and Third Quarters of the year 2018.

Figure 3.1: Bar Chart Showing Quarterly Total Expenditure Performance

Figure 3.1 above compares the total actual expenditure for the first, second and third quarters of year 2018 with the quarterly estimates. The total actual expenditure for the third quarter was N26.117 billion against the proposed estimates of N45.356 billion. This represents a 57.6% overall performance level for the quarter while in the first quarter, the overall performance was 47.5% and 49.6% for the second quarter.

Figure 3.2: Bar Chart Showing Quarterly Performance of Expenditure Classifications

Figure 3.2 above shows the performance of the expenditure classifications for the first, second and third quarters of the year 2018 against the quarterly estimates. The actual expenditures for the three quarters were compared with the proposed quarterly estimates. The actual recurrent expenditure for the third quarter was N19.146 billion against the proposed estimates of N19.647 billion, representing 97.4% performance level for the quarter while in the first quarter, the performance was 78.5% and 85.0% for the second quarter.

The third quarter estimates for debt repayment stood at N3.400 billion. At the end of the quarter, actual debt repayment figure furnished by the Debt Management Office was N1.544 billion, showing a 45.4% performance level for the quarter while in the first quarter, the performance was 75.9% and 45.3% for the second quarter.

In similar manner, the proposed estimates for statutory transfer in the third quarter of the year was N2.077 billion. At the end of the quarter, actual statutory transfer was N1.625 billion, representing 78.2% performance level for the quarter while in the first quarter, the performance was 36.9% and 89.3% for the second quarter.

Also, actual capital expenditure was N3.803 billion against the quarterly estimates of N20.232 billion, performing at 18.8% level while in the first quarter, the performance was 13.6% and 11.9% for the second quarter.

Figure 3.3: Pie Chart Showing Share of Third Quarter Actual Expenditure

Figure 3.3 above shows the representative proportions of the actual total expenditure for the third quarter of the year 2018. Out of the estimates of N45.356 billion for the quarter, the sum of N26.117 billion was recorded as the actual total expenditure for the third quarter of the year 2018, representing a 57.6% overall performance level. Specifically, actual recurrent expenditure was 73%, actual debt repayment 6%, actual statutory transfer 6% and actual capital expenditure 15% for the quarter.

  - RECURRENT EXPENDITURE ANALYSIS

Analysis of recurrent expenditure for the third quarter shows that the actual recurrent expenditure for the quarter was N19.146 billion against the proposed estimates of N19.647 billion for the quarter. This figure showed that recurrent expenditure performed at 97.4% level for the quarter while in the first quarter, the performance was 78.5% and 85.0% for the second quarter.

Table 3.3: Details of Quarterly Recurrent Expenditure Components

| S/N | EXPENDITURE DETAILS | QUARTERLY ESTIMATES (N) | FIRST QUARTER ACTUAL (N) | SECOND QUARTER ACTUAL (N) | THIRD QUARTER ACTUAL (N) |
| --- | --- | --- | --- | --- | --- |
| 1 | PERSONNEL COST | 9,477,490,500.00 | 7,922,604,467.29 | 8,629,192,940.34 | 8,489,554,539.75 |
| 2 | OVERHEAD COST | 1,122,322,375.00 | 781,682,376.65 | 1,001,709,911.30 | 893,618,741.49 |
| 3 | SPECIAL PROGRAMME | 4,077,813,575.00 | 2,035,929,337.84 | 2,200,655,856.46 | 3,165,143,100.95 |
| 4 | GRANTS TO PARASTATALS/SUBVENTION | 1,806,792,421.52 | 919,742,037.50 | 1,244,867,337.50 | 2,458,784,584.00 |
| 5 | CONSOLIDATED REVENUE FUND CHARGE | 3,125,000,000.00 | 3,735,999,309.07 | 3,592,314,385.46 | 4,103,021,833.73 |
| 6 | GRANTS/LOANS | 37,500,000.00 | 35,465,600.00 | 26,599,200.00 | 35,465,600.00 |
|  | TOTAL RECURRENT EXPENDITURE | 19,646,918,871.52 | 15,431,423,128.35 | 16,695,339,631.06 | 19,145,588,399.92 |

SOURCE: Office of Accountant General and Debt Management Office, Ondo State

Table 3.3 above shows the summary of the recurrent expenditure components for the third quarter of the year 2018. The third quarter estimates for Personnel Cost was N9.477 billion, Overhead Cost N1.122 billion, Special Programme N4.077 billion, Grants to Parastatals/Subvention N1.806 billion, Consolidated Revenue Fund Charges N3.125 billion and N0.037 billion as Grants/Loans. At the end of the quarter, the actual of these recurrent expenditure components, in the same order, were N8.490 billion, N0.894 billion, N3.165 billion, N2.459 billion, N4.103 billion and N0.035 billion, representing 89.6%, 79.6%, 77.6%, 136.1%, 131.3% and 94.6% performance levels respectively for the quarter.

Figure 3.4: Bar Chart Showing Quarterly Recurrent Expenditure

Components

Figure 3.5: Pie Chart Showing Share of Third Quarter Actual Recurrent Expenditure Components

Figure 3.5 above shows the representative proportions of the actual recurrent expenditure components for the third quarter of the year 2018. Out of the actual total recurrent expenditure of N19.146 billion recorded for the third quarter of the year, Personnel cost accounted for 44%, Overhead Cost 5%, Special Programme 17%, Grants to Parastatals/Subvention 13%, Consolidated Revenue Fund Charges 21% and Grants/Loans 0.001% respectively for the quarter.

PERSONNEL COST

With quarterly estimates of N9.477 billion, actual personnel cost for the third quarter was N8.490 billion, representing 89.6% performance level for the quarter while the first quarter performance was 83.6% and 91.0% for the second quarter.

Figure 3.6: Bar Chart Showing Quarterly Personnel Cost

Table 3.4: Details of Quarterly Personnel Cost

| S/N | PERONNEL DETAILS | SECOND QUARTER ACTUAL (N) | THIRD QUARTER ACTUAL (N) |
| --- | --- | --- | --- |
| 1 | CORE CIVIL SERVICE | 4,379,931,120.15 | 4,300,839,175.09 |
| 2 | ADHOC HMB STAFF | 106,543,555.26 | 104,168,989.96 |
| 3 | ADHOC MIN. OF AGRIC STAFF | 1,697,089.62 | 626,083.42 |
| 4 | TESCOM (PUB. SECONDARY SCH) | 3,741,154,300.84 | 3,694,056,163.91 |
| 5 | JUDICIAL | 399,866,874.47 | 389,864,127.37 |
|  | TOTAL | 8,629,192,940.34 | 8,489,554,539.75 |

SOURCE: OFFICE OF ACCOUNTANT GENERAL, ONDO STATE

Table 3.4 above shows the personnel cost details for the second and third quarters of the year 2018. In the classifications of Core Civil Service, Adhoc Hospitals’ Management Board (HMB) Staff, Adhoc Ministry of Agriculture Staff, Teaching Service Commission (TESCOM) Public Secondary School and the Judicial, the actual personnel cost for Core Civil Service for the third quarter was N4.301 billion, Adhoc HMB Staff N0.104 billion, Adhoc Ministry of Agriculture Staff N0.626 million, TESCOM Public Secondary School N3.694 billion and the Judicial N0.390 billion.

Figure 3.7: Pie Chart Showing Share of Third Quarter Personnel Cost Details

Figure 3.7 above shows the representative proportions of the actual personnel cost for the third quarter of the year 2018. Out of the actual personnel cost of N8.490 billion recorded for the third quarter of the year, Core Civil Service accounted for 51%, Adhoc HMB Staff 1%, Adhoc Ministry of Agriculture Staff 0.001%, TESCOM Public Secondary School 43% and the Judicial 5%.

    - OVERHEAD COST

With quarterly estimates of N1.122 billion, actual overhead cost for the third quarter was N0.894 billion, representing 79.6% performance level for the quarter while the first quarter performance was 69.6% and 89.3% for the second quarter.

Figure 3.8: Bar Chart Showing Quarterly Overhead Cost

    - SPECIAL PROGRAMMES

The quarterly estimates for this head was N4.078 billion. At the end of the third quarter, the actual expenditure recorded was N3.165 billion, representing a 77.6% performance level while the first quarter performance was 49.9% and 54.0% for the second quarter.

Figure 3.9: Bar Chart Showing Quarterly Special Programme.

    - SUBVENTIONS/GRANTS TO INSTITUTIONS AND AGENCIES

The quarterly estimates for this head was N1.807 billion. At the end of the third quarter, the actual expenditure recorded was N2.458 billion, representing a 136.1% performance level while the first quarter performance was 50.9% and 68.9% for the second quarter.

Table 3.5: Summary of Quarterly Subvention/Grants to Parastatals

| S/N | INSTITUTIONS | QUARTERLY ESTIMATES (N) | FIRST QUARTER ACTUAL (N) | SECOND QUARTER ACTUAL (N) | THIRD QUARTER ACTUAL (N) |
| --- | --- | --- | --- | --- | --- |
| 1 | Adekunle Ajasin University, Akungba Akoko | 482,792,421.52 | 297,500,000.00 | 446,250,000.00 | 595,000,000.00 |
| 2 | Nigeria Security and Civil Defence Corps | 500,000.00 | 116,200.00 | 348,600.00 | 464,800.00 |
| 3 | Nigerian Legion | 1,000,000.00 | 420,000.00 | 630,000.00 | 840,000.00 |
| 4 | Ondo State Agency for Road Maintenance and Construction (OSAMCO) | 12,500,000.00 | 4,666,200.00 | 4,666,200.00 | 9,332,400.00 |
| 5 | Ondo State Football Academy | 20,000,000.00 | - | - | - |
| 6 | Ondo State Football Development Agency | 162,500,000.00 | 90,000,000.00 | 113,258,537.50 | 180,000,000.00 |
| 7 | Ondo State University of Medical Sciences | 150,000,000.00 | 90,000,000.00 | 90,000,000.00 | 180,000,000.00 |
| 8 | Ondo State University of Science and Technology, Okitipupa | 194,250,000.00 | 84,000,000.00 | 126,000,000.00 | 233,000,000.00 |
| 9 | Rufus Giwa Polytechnic, Owo | 717,500,000.00 | 299,026,000.00 | 448,539,000.00 | 1,259,447,384.00 |
| 10 | Senior Staff Club | 750,000.00 | 350,000.00 | 350,000.00 | 700,000.00 |
| 11 | Ondo State Investment Promotion Agency (ONDIPA) | 50,000,000.00 | - | - | - |
| 12 | Ondo State Radiovision Corporation | 12,500,000.00 | 12,698,037.50 | 5,750,437.50 | - |
| 13 | Ondo State Afforestation Project | 2,500,000.00 | - | - | - |
| 14 | Ondo State Water Corporation | - | - | 9,074,562.50 | - |
|  | TOTAL | 1,806,792,421.52 | 919,742,037.50 | 1,244,867,337.50 | 2,458,784,584.00 |

SOURCE: OFFICE OF ACCOUNTANT GENERAL, ONDO STATE

Figure 3.10: Bar Chart Showing Quarterly Subventions to Institutions and Agencies

    - CONSOLIDATED REVENUE FUND CHARGES (CFRC)

With quarterly estimates of N3.125 billion, actual CRFC for the third quarter was N4.103 billion, representing 131.3% performance level for the quarter while the first quarter performance was 119.6% and 115.0% for the second quarter.

Table 3.6: Details of Quarterly Consolidated Revenue Funds Charge (CRFC)

| S/N | CRFC DETAILS | QUARTERLY ESTIMATES (N) | FIRST QUARTER ACTUAL (N) | SECOND QUARTER ACTUAL (N) | THIRD QUARTER ACTUAL (N) |
| --- | --- | --- | --- | --- | --- |
| 1 | PENSION | 802,183,644.25 | 1,893,381,380.11 | 1,939,345,288.98 | 2,007,733,270.14 |
| 2 | SALARIES OF POLITICAL OFFICE HOLDERS | 414,794,777.25 | 130,704,659.65 | 149,084,931.21 | 149,169,438.12 |
| 3 | GRATUITY | 375,000,000.00 | 720,000,000.00 | 731,487,054.64 | 1,179,635,285.76 |
| 4 | DIRECT DEDUCTION FROM FAAC | 1,376,222,930.02 | 991,913,269.31 | 772,397,110.63 | 766,483,839.71 |
| 5 | CONTRIBUTORY PENSION (EMPLOYERS) | 150,548,648.49 | - | - | - |
| 6 | PAYMENT OF BENEFITS TO PAST GOVERNORS/DEPUTY GOVERNORS | 6,250,000.00 | - | - | - |
|  | TOTAL | 3,125,000,000.01 | 3,735,999,309.07 | 3,592,314,385.46 | 4,103,021,833.73 |

Source: Office of the Accountant-General/Debt Management Department

Figure 3.11: Bar Chart Showing Quarterly Consolidated Revenue Fund Charges (CRFC)

Figure 3.11 above compares the performance of the CRFC components for the first, second and third quarters of the year 2018 against the quarterly estimates. The quarterly estimates for Pension was N0.802 billion, Salaries of Political Office holders N0.415 billion, Gratuity N0.375 billion, Interest component of Direct Deduction from FAAC N1.376 billion, Contributory Pension (Employers) N0.151 billion and Payment of Benefits to Past Governors/Deputy Governors N0.006 billion. At the end of the third quarter, the actual of the expenditure components, in the same order, were N2.008 billion, N0.149 billion, N1.180 billion, N0.766billion, N0.000 billion and N0.000 billion.

    - GRANTS/LOAN

The quarterly estimates for Grants/Loan was N37.500 million. At the end of the third quarter, the actual expenditure recorded for this head was N35.465 million, representing a 94.6% performance level while in the first quarter, the performance was 94.6% and 70.9% for the second quarter.

Figure 3.12: Bar Chart Showing Quarterly Grants/Loan

  - SECTORAL RECURRENT EXPENDITURE ANALYSIS

Table 3.7 below shows the sectoral recurrent expenditure details for the first, second and third quarters of the year 2018. In the classifications of Economic sector, Social Services Sector, Law & Justice Sector Administration Sector and Consolidated Revenue Fund Charges, the Social services sector recorded the highest actual recurrent expenditure of N9.339 billion, representing 106.8% performance level in the third quarter. On the other hand, Administration Sector recorded the least performance at 41.3% level in the third quarter of 2018.

Table 3.7:  Quarterly Sectoral Recurrent Expenditure Details

| S/N | Sub-Sector/SECTOR | QUARTERLY ESTIMATES (N) | FIRST QUARTER ACTUAL (N) | SECOND QUARTER ACTUAL (N) | THIRD QUARTER ACTUAL (N) |
| --- | --- | --- | --- | --- | --- |
| 1 | Agric | 396,511,113.00 | 313,111,748.10 | 325,548,787.35 | 317,630,477.72 |
| 2 | Trade & Industry | 159,491,529.13 | 106,161,621.28 | 97,094,134.22 | 141,667,463.34 |
| 3 | Infrastructure | 711,453,797.97 | 454,628,048.44 | 522,954,880.92 | 467,145,315.06 |
| 4 | Public Finance | 1,807,536,279.21 | 1,389,837,384.86 | 1,492,903,620.54 | 2,417,276,893.24 |
| A | TOTAL ECONOMIC SECTOR | 3,074,992,719.31 | 2,263,738,802.68 | 2,438,501,423.03 | 3,343,720,149.36 |
| 1 | Education | 6,120,158,193.23 | 4,995,028,551.16 | 5,510,743,557.81 | 6,606,918,809.77 |
| 2 | Health | 2,064,311,052.91 | 2,017,198,406.46 | 2,245,982,917.06 | 2,161,260,329.89 |
| 3 | Social & Community Development | 434,432,044.45 | 558,339,835.76 | 318,946,078.28 | 440,086,543.02 |
| 4 | Environment & Sewage Management | 127,444,392.96 | 94,587,240.85 | 122,410,833.47 | 131,085,488.64 |
| B | TOTAL SOCIAL SERVICES SECTOR | 8,746,345,683.55 | 7,665,154,034.23 | 8,198,083,386.62 | 9,339,351,171.32 |
| 1 | Administration of Justice | 544,618,810.71 | 117,191,575.54 | 548,548,121.40 | 644,576,967.57 |
| C | TOTAL LAW & JUSTICE SECTOR | 544,618,810.71 | 117,191,575.54 | 548,548,121.40 | 644,576,967.57 |
| 1 | General Administration | 3,161,192,886.12 | 1,034,851,917.68 | 1,152,471,385.57 | 1,118,550,794.11 |
| 2 | Legislative | 725,362,184.77 | 429,323,502.29 | 588,077,647.80 | 398,577,533.23 |
| 3 | Information | 269,406,587.08 | 144,531,720.20 | 159,610,481.18 | 197,789,950.60 |
| D | TOTAL ADMINISTRATION SECTOR | 4,155,961,657.96 | 1,608,707,140.17 | 1,900,159,514.55 | 1,714,918,277.94 |
| E | CONSOLIDATED REVENUE FUND CHARGES | 3,125,000,000.00 | 3,735,999,309.07 | 3,592,314,385.46 | 4,103,021,833.73 |
|  | GRAND TOTAL (A+B+C+D+E) | 19,646,918,871.52 | 15,431,423,128.35 | 16,695,339,631.06 | 19,145,588,399.92 |

Source: Office of the Accountant-General, Ondo State.

Figure 3.13: Bar Chart Showing Quarterly Sectoral Recurrent Expenditure

  - STATUTORY TRANSFERS

With quarterly estimates of N2.077 billion, actual Statutory Transfers to OSOPADEC and Local Governments for the third quarter was N1.625 billion, representing 78.2% performance level for the quarter while first quarter performance was 36.9% and 89.3% for the second quarter.

Table 3.8: Details of Quarterly Statutory Transfers

| S/N | PARTICULARS | QUARTERLY ESTIMATES (N) | FIRST QUARTER ACTUAL (N) | SECOND QUARTER ACTUAL (N) | THIRD QUARTER ACTUAL (N) |
| --- | --- | --- | --- | --- | --- |
| 1 | TRANSFER TO LOCAL GOVERNMENT JOINT ACCOUNT (10%) | 523,341,169.58 | 127,868,122.86 | 133,982,328.17 | 145,711,156.69 |
| 2 | TRANSFER TO OSOPADEC | 1,553,659,200.00 | 639,125,944.35 | 1,721,554,600.17 | 1,479,147,014.34 |
|  | TOTAL | 2,077,000,369.58 | 766,994,067.21 | 1,855,536,928.34 | 1,624,858,171.03 |

Source: Office of the Accountant-General

Figure 3.14: Bar Chart Showing Quarterly Statutory Transfer

  - CAPITAL EXPENDITURE ANALYSIS

The quarterly estimates for Capital expenditure was N20.232 billion. At the end of the third quarter, the actual capital expenditure recorded was N3.803 billion, representing 18.8% overall performance level while in the first quarter, the performance was 13.6% and 11.9%  for the second quarter.

Table 3.9:  Quarterly Sectoral Capital Expenditure Details

| S/N | Sub-Sector/SECTOR | QUARTERLY ESTIMATES (N) | FIRST QUARTER ACTUAL (N) | SECOND QUARTER ACTUAL (N) | THIRD QUARTER ACTUAL (N) |
| --- | --- | --- | --- | --- | --- |
| 1 | Agric | 2,177,446,250.00 | 314,174,678.49 | 182,443,975.94 | 83,869,450.00 |
| 2 | Trade & Industry | 951,250,000.00 | 962,000.00 | 214,388,464.76 | 105,920,002.00 |
| 3 | Infrastructure | 5,945,790,000.00 | 2,225,969,857.47 | 1,453,640,535.88 | 2,949,043,232.99 |
| 4 | Public Finance | 726,500,000.00 | 67,211,962.00 | 92,410,520.54 | 103,466,741.15 |
| A | TOTAL ECONOMIC SECTOR | 9,800,986,250.00 | 2,608,318,497.96 | 1,942,883,497.12 | 3,242,299,426.14 |
| 1 | Education | 3,510,646,592.00 | 21,700,520.00 | 113,611,518.77 | 73,100,000.00 |
| 2 | Health | 1,845,783,695.75 | 16,530,000.00 | 86,317,680.00 | 96,006,000.00 |
| 3 | Social & Community Development | 625,750,000.00 | - | 2,315,142.07 | 5,976,584.00 |
| 4 | Environment & Sewage Management | 452,500,000.00 | 719,000.00 | 33,744,541.92 | 52,401,555.00 |
| B | TOTAL SOCIAL SERVICES SECTOR | 6,434,680,287.75 | 38,949,520.00 | 235,988,882.76 | 227,484,139.00 |
| 1 | Administration of Justice | 364,250,000.00 | 11,278,237.50 | 50,302,549.08 | 87,575,999.79 |
| C | TOTAL LAW & JUSTICE SECTOR | 364,250,000.00 | 11,278,237.50 | 50,302,549.08 | 87,575,999.79 |
| 1 | General Administration | 3,400,707,520.75 | 55,412,760.79 | 172,725,871.61 | 185,083,688.86 |
| 2 | Legislative | 128,372,250.00 | 20,830,000.00 |  | 6,789,601.89 |
| 3 | Information | 103,250,000.00 | 19,964,425.00 | 14,695,414.80 | 54,210,663.66 |
| D | TOTAL ADMINISTRATION SECTOR | 3,632,329,770.75 | 96,207,185.79 | 187,421,286.41 | 246,083,954.41 |
|  | GRAND TOTAL (A+B+C+D) | 20,232,246,308.50 | 2,754,753,441.25 | 2,416,596,215.37 | 3,803,443,519.34 |

SOURCE: OFFICE OF ACCOUNTANT GENERAL, ONDO STATE

Figure 3.15: Bar Chart Showing Quarterly Sectoral Capital Expenditure

Figure 3.15 above shows that the Economic Sector accounted for the highest actual capital expenditure of N3.242 billion, representing a 33.1% performance level. On the other hand, Law & Justice Sector, with least actual expenditure of N0.087 billion recorded a 24.1% performance level for the third quarter of 2018.

CHAPTER FOUR

STATUS OF CAPITAL PROJECTS AWARDED BETWEEN JANUARY AND SEPTEMBER, 2018

The 2018 Budget tagged “Budget of Progress” was designed to focus on rebuilding the State’s economy through prioritised investment on infrastructural facilities and agriculture-related activities. It was also prepared to strengthen partnership between public and private sector as well as Development Partners to leverage and catalyze resources for growth. In order to achieve the objectives of the cardinal programme of this Administration, a sum of N80.929 billion was budgeted for capital expenditure in 2018.

Findings from the Mid-Year Budget Appraisal revealed that a total of 704 projects was awarded between January and June, amounting to N41.979 billion based on the contract award documents from the Cabinet and Special Services Department. At the time of completion of the Mid-Year Budget Appraisal, the status of most of the projects awarded were unknown to the Monitoring and Evaluation Department of the Ministry of Economic Planning and Budget. Hence, this section provides the Status of the Capital projects as at September 2018.

The MEDAs executing these projects are: State Universal Basic Education Board (SUBEB), Ministry of Works and Infrastructure, Ondo State Oil Producing Areas Development Commission (OSOPADEC) and Ministry of Information and Orientation.

Table 4.1: Summary of Projects Awarded from January-September, 2018.

| S/N | MEDAs | PROJECTS | TOTAL SUM N | ACTUAL PAYMENT N | PERFORMANCE LEVEL (%) |
| --- | --- | --- | --- | --- | --- |
| 1 | State Universal Basic Education Board | 599 | 7,102,012,331.63 | 4,855,477,115.21 | 68.4 |
| 2 | Ministry of Works and Infrastructure | 15 | 23,902,350,399.49 | 2,523,682,224.33 | 10.6 |
| 3 | Ministry of Information and Orientation | 1 | 23,099,000.00 | 22,023,800.00 | 95.3 |
| 4 | Ondo State Oil Producing Areas Development Commission | 90 | 11,009,820,961.63 | 426,062,212.42 | 3.9 |
|  | TOTAL | 705 | 42,037,282,692.75 | 7,827,245,351.96 | 18.6 |

Source: Cabinet and Special Services Department, Governor Office, Ondo State

4.1	Analysis Of Projects Implemented By State Universal Basic

Education Board (SUBEB)

The State Universal Basic Education Board (SUBEB) awarded 599 projects, amounting to N7.1 billion. At the end of September, 2018, the sum of N4.855 billion, representing 68 percent of contract sum of the projects have been paid to the contractors. These projects were classified into: Construction/Renovation of Block of Classrooms, Construction of Perimeter Fence, Purchase & Supply of ICT Facilities, Purchase and Supply of Play Ground Equipment, Supply and Put in Place Pupils Furniture, Provision of Borehole, Containerised Toilet and Supply and Put in Place ECCDE Furniture to selected schools. The execution of these projects in primary schools cut across all the eighteen Local Government Areas (LGAs) in the State.

Table 4.2 Classification of the UBEC/SUBEB 599 Projects

| S/N | PROGRAMME/PROJECT DESCRIPTION | NO OF PROJECTS | CONTRACT SUM | AMOUNT REALEASED AS AT SEPTEMBER, 2018 |
| --- | --- | --- | --- | --- |
| 1 | Supply and put in place ECCDE Furniture to selected Schools | 5 | 7,394,509.34 | 7,394,509.34 |
| 2 | Construction of classrooms and perimeter fence | 139 | 3,079,456,529.05 | 2,175,362,895.57 |
| 3 | Containerised Toilets | 77 | 525,810,498.36 | 75,525,103.61 |
| 4 | Renovation of Classrooms block | 257 | 2,860,052,679.21 | 2,196,851,968.30 |
| 5 | Supply and put in place Pupils Furniture | 42 | 263,960,127.85 | 235,022,676.82 |
| 6 | Purchase and supply Information Technology facilities (Computer System and other Accessories) | 41 | 171,335,886.31 | 55,885,463.21 |
| 7 | Purchase and Supply Play Ground Equipment | 30 | 165,437,701.51 | 94,610,052.33 |
| 8 | Installation/ provision of Boreholes | 8 | 28,564,400.00 | 14,824,446.03 |
|  | TOTAL | 599 | 7,102,012,331.63 | 4,855,477,115.21 |

Source: Cabinet and Special Services Department, Governor Office, Ondo State

In the table 4.2 above, 257 projects were for renovation of classrooms blocks ranging from 2 to 6 block of classrooms, with a  contract sum of N2.860 billion, and an actual payment of N2.196 billion at the end of September, 2018. Construction of classrooms block and perimeter fence  were 139 projects with the contract sum of N3.079 billion, and N2.175 billion as actual payment at the end of September, 2018.

Table 4.3: Status of SUBEB Projects

| Percentage of work done | No of projects | Contract sum | Actual payment till September, 2018 |
| --- | --- | --- | --- |
| 100 | 193 | 1,858,404,245.93 | 1,654,899,319.63 |
| 90-99 | 127 | 2,145,975,606.20 | 1,691,271,235.41 |
| 80-89 | 58 | 900,236,702.15 | 641,115,429.96 |
| 70-79 | 37 | 526,293,817.31 | 302,798,923.61 |
| 60-69 | 36 | 528,969,330.30 | 258,598,621.36 |
| 50-59 | 17 | 230,340,252.42 | 88,327,003.20 |
| 40-49 | 10 | 119,211,552.93 | 60,705,835.23 |
| 30-39 | 4 | 49,631,692.44 | 24,739,382.13 |
| 20-29 | 2 | 39,982,461.29 | 1,111,654.10 |
| 10-19 | 1 | 6,466,837.00 | 5,655,000.24 |
| 0-9 | 107 | 632,353,342.88 | 91,062,258.79 |
| not specify | 7 | 64,146,490.78 | 35,192,451.55 |
| Total | 599 | 7,102,012,331.63 | 4,855,477,115.21 |

Figure 4.1: Bar Chart Showing Status of SUBEB Projects

Table 4.3 and Figure 4.1 showed that 193 projects, representing 32 percent of the total projects have been completed as at September, 2018. 127 projects were ranging from 90 to 99 level of completion while 107 of projects were still less than ten percent level of completion. 106 of the projects which were yet to commence as at the time of this report were majorly Containerised Toilet, Purchase and supply Information facilities (Computer System and other Accessories), Purchase and Supply of Play Ground Equipment and Installation of Boreholes while 7 projects level of completion were not specified.

4.2  Analysis Of Projects Implemented By Ondo State Oil

Producing Areas Development Commission (OSOPADEC)

The Ondo State Oil Producing Areas Development Commission awarded 90 projects, amounting to N11.001 billion. As at September 2018, a sum of N0.426 billion has been expended on the projects. The execution of the projects were in Ilaje, Ese Odo, Irele and Okitipupa LGAs in the Southern Senatorial District of the State. The projects include the Repair/Rehabilitation of Wooden Walkways & Jetties and Construction of roads in the areas.

Table 4.4: Status of OSOPADEC Projects

| PERCENTAGE OF WORK DONE | NO OF PROJECTS | CONTRACT SUM | ACTUAL PAYMENT TILL SEPTEMBER, 2018 |
| --- | --- | --- | --- |
| 100 | 3 | 19,025,117.57 | 5,707,535.27 |
| 90-99 | 2 | 1,344,401,845.87 | 160,168,338.82 |
| 80-89 | 9 | 65,906,554.96 | 19,771,962.48 |
| 70-79 | 7 | 87,244,388.79 | 26,973,316.67 |
| 60-69 | 7 | 66,783,425.57 | 18,070,824.92 |
| 50-59 | 5 | 52,450,086.22 | 15,745,225.87 |
| 40-49 | 6 | 59,110,681.11 | 12,960,762.82 |
| 30-39 | 5 | 47,044,855.94 | 14,913,456.78 |
| 20-29 | 3 | 31,963,363.53 | 9,589,009.06 |
| 10-19 | 11 | 105,918,435.89 | 32,190,497.93 |
| 0-9 | 32 | 9,129,972,206.18 | 109,971,281.80 |
| TOTAL | 90 | 11,009,820,961.63 | 426,062,212.42 |

Figure 4.2:  Bar chart Showing Status of OSOPADEC Projects.

Table 4.4 and Figure 4.2 showed that 3 out 90 projects were 100 percent completed while 32 of the projects were at the level of commencement and minimal significant work done.

4.3	Analysis of Projects Implemented By Ministry of Works and

Infrastructure

In similar manner, Ministry of Works and Infrastructure awarded 15 projects, amounting to N23.902 billion. As at the end of September, 2018. The total of N2.247 billion, representing 9.5 percent actual payment on the projects have been made. These projects were majorly dualisation of township roads, construction and rehabilitation of selected township roads.

Table 4.5: Status of Projects by Ministry of Works and

Infrastructure

| PERCENTAGE OF WORK DONE | NO OF PROJECTS | CONTRACT SUM | ACTUAL PAYMENT TILL SEPTEMBER, 2018 |
| --- | --- | --- | --- |
| 90-99% | 5 | 2,639,534,731.86 | 1,160,662,637.06 |
| 80-89% | 1 | 499,178,285.18 | 381,821,344.79 |
| 70-79% | 1 | 681,860,851.77 | 14,367,260.69 |
| 50-59% | 1 | 629,068,880.99 |  |
| 30-39% | 1 | 1,135,947,260.02 |  |
| 20-29% | 2 | 1,190,060,938.96 | 9,119,082.28 |
| 10-19% | 3 | 11,613,939,031.89 | 957,711,899.51 |
| 0-9% | 1 | 5,512,760,418.82 |  |
| Total | 15 | 23,902,350,399.49 | 2,523,682,224.33 |

Table 4.5 revealed that 7 of the projects were substantially completed ranging from 75 to 95 percent level of completion while another 7 projects ranged from 0 to 30 percent level of completion.

CHAPTER FIVE

OBSERVATIONS, RECOMMENDATIONS AND CONCLUSION

5.1	OBSERVATIONS

The following are the observations from the third quarter budget implementation appraisal:

- Overall Budget performance was above average in the third quarter, as revenue witnessed a slight increase over the previous quarter values.

- The revenue side of the budget performed at 59.4% in the third quarter.

- Revenue receipts from the Federation Account was N18.167 billion, representing 68% of total revenue for the third quarter.

- Actual receipts from Statutory Allocation exceeded expected targets for the three quarters, recording 149%, 150.77% and 161.96% performance levels for first, second and third quarters respectively.

- Actual revenue from Mineral Derivation also recorded surplus over expected target for the three quarters, performing at 125.49%, 113.75% and 107.29% levels for first, second and third quarters respectively.

- The share of Internally Generated Revenue to total actual revenue was 15 percent for the third quarter.

- Internally Generated Revenue performed at 96.0% in the third quarter.

- The third quarter total Independent Revenue performance of 96% was inclusive of amount generated by the Revenue Retaining Agencies (RRA). Less the RRA, the performance was 78.44%

- Targets were not set for some Revenue Heads in the Approved 2018 Budget of the State. These Revenue Heads are: Revenue Retaining Agencies (RRA), Excess Bank Charges and Fixed Deposit Recalls.

- The expenditure side of the budget performed above average at 57.6% in the third quarter.

- Capital expenditure rose slightly to the tune of N3.803 billion in the third quarter, witnessing an increase of 57.4% over second quarter value.

- Share of Recurrent expenditures accounted for 73% of the total actual expenditures for the third quarter, with capital expenditure share at 15% for the period.

- The total debt repayment made for the third quarter was N1.544 billion, representing 7% of the total expenditure.

- Statutory transfers to OSOPADEC and Local Governments was N1.625 billion in the third quarter, recording a 12.4% decrease for the period.

- 193 UBEC/SUBEB projects representing 32 percent of the total UBEC/SUBEB projects have been completed as at September, 2018 with another 127 projects ranging from 90 to 99 level of completion.

- 106 UBEC/SUBEB projects were yet to commence as at the time of this report. These were majorly Containerised Toilet, Purchase and supply Information facilities (Computer System and other Accessories), Purchase and Supply of Play Ground Equipment and Installation of Boreholes.

- Three (3) out of Ninety (90) OSOPADEC projects have been completed while 32 of the projects were at 0 - 9 percent level of work done.

- Seven (7) of the projects were substantially completed ranging from 75 to 95 percent level of completion while another Seven (7) projects ranged from 0 to 30 percent level of completion.

- Late submission of returns by MEDAs is still a challenge causing delay in the timely preparation of the Budget Implementation Appraisal.

5.2	RECOMMENDATIONS

- While commending the efforts of the apex revenue generating agency, more emphasis should be placed on shoring up the Internally Generated Revenues (IGR) of the State, through aggressive tax campaign, expansion of the tax bracket, ease of payment and collection of levies e.t.c.

- More efforts should be geared towards attracting Development Partners and Donors to the State so as to complement the financing of the various developmental projects in the State.

- The State Government should strengthen its Public-Private Partnership Initiatives. This will, in no small measure, increase the development in the State.

- Though improving, more attention should still be given to capital budget implementation in the rest of the year and beyond.

- Targets should be set for those revenue heads without targets in the Approved 2018 budget so that their performance can be appropriately measured.

- There is need to fast track processes of fund release to some of the OSOPADEC projects not yet implemented due to non-release of funds.

- Measures should be put in place to ensure that  the 106 UBEC/SUBEB projects yet to commence are kickstarted.

- The Monitoring and Evaluation Department of the Ministry of Economic Planning and Budget should be given necessary support to conduct monitoring exercise on regular basis in order to determine the status of the projects and advise the government appropriately.

5.3	CONCLUSION

The budget performance appraisal for the third quarter recorded a slight and better performance than the previous quarters. Both revenue and expenditure performed above average in the period under review. While appreciating the performance, there is still room for more measures to be taken to further improve budget performance in the State.

In conclusion, efforts should be channelled towards addressing the observations and implementing the recommendations provided in the 2018 Third Quarter Budget Appraisal for a better budget performance in the rest of the year and beyond.

APPENDIX

Table I: Details of MEDAs Recurrent and Capital Expenditure

| S/N | SECTOR/MDAs/INSTITUTIONS | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| A | ECONOMIC SECTOR | THIRD QUARTER ESTIMATES | THIRD QUARTER ACTUAL | THIRD QUARTER ESTIMATES | THIRD QUARTER ACTUAL |  |
| A1 | AGRIC SUB SECTOR |  |  |  |  |  |
| 1 | Ministry of Natural Resources | 166,275,254.26 | 142,417,891.51 | 79,875,000.00 | 10,575,350.00 |  |
| 2 | Ondo State Afforestation Project | 2,500,000.00 | - | - | - |  |
| 3 | Ondo State Rural Access and Mobility Project (Community Based Urban Development Project | 2,000,000.00 | 900,000.00 | 800,000,000.00 | 705,000.00 |  |
| 4 | Accelerated Poverty Alleviation Agency (APAA) | 2,520,000.00 | 900,000.00 | 257,500,000.00 | 7,037,000.00 |  |
| 5 | Ministry of Agriculture | 129,223,127.03 | 92,137,065.07 | 681,700,000.00 | 48,272,100.00 |  |
| 6 | Forestry Training School, Owo | 101,250.00 | 66,426.00 | - | - |  |
| 7 | Agric Development Programme | 69,069,164.18 | 60,341,279.58 | 260,871,250.00 | 4,380,000.00 |  |
| 8 | Agric Input and Supply Agency | 16,432,317.53 | 16,292,815.56 | 17,500,000.00 | 5,850,000.00 |  |
| 9 | Agroclimatology & Ecological Project | 1,650,000.00 | 825,000.00 | 5,000,000.00 | 850,000.00 |  |
| 10 | Cocoa Revolution Office | 990,000.00 | 750,000.00 | 75,000,000.00 | 6,200,000.00 |  |
| 11 | Fadama Project | 2,250,000.00 | 1,500,000.00 | - | - |  |
| 12 | Ondo State UN-REDD+ Project | 3,500,000.00 | 1,500,000.00 | - | - |  |
|  | SUB TOTAL: Agric-sub sector | 396,511,113.00 | 317,630,477.72 | 2,177,446,250.00 | 83,869,450.00 |  |
| A2 | TRADE AND INDUSTRY SUB SECTOR | - | - | - |  |  |
| 13 | Ministry of Commerce, Industries and Cooperatives | 36,348,694.24 | 43,079,505.91 | 424,000,000.00 | 9,472,000.00 |  |
| 14 | Consumer Protection Committee | 917,500.00 | 562,500.00 | - | - |  |
| 15 | Micro Credit Agency | 9,653,734.72 | 9,079,757.81 | 2,500,000.00 | 410,000.00 |  |
| 16 | Co-operative College, Akure | 81,000.00 | - | - | - |  |
| 17 | Ministry of Employment and Productivity | - | 3,100,038.90 | - | - |  |
| 18 | Ondo State Investment Promotion Agency (ONDIPA) | 50,000,000.00 | 50,000,000.00 | 500,000,000.00 | 86,850,500.00 |  |
| S/N | SECTOR/MDAs/INSTITUTIONS | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |  |
|  |  | THIRD QUARTER ESTIMATES | THIRD QUARTER ACTUAL | THIRD QUARTER ESTIMATES |  | THIRD QUARTER ACTUAL |
|  | Free Trade Zone | - | - | - | - |  |
| 19 | Ministry of Culture and Tourism | 62,490,600.17 | 35,845,660.72 | 24,750,000.00 | 9,187,502.00 |  |
|  | SUB TOTAL: Trade and Industry Sub-Sector | 159,491,529.13 | 141,667,463.34 | 951,250,000.00 | 105,920,002.00 |  |
| A3 | INFRASTRUCTURAL SUB SECTOR |  |  |  |  |  |
| 20 | Office of Transport | 111,382,841.89 | 97,565,077.29 | 50,000,000.00 | 2,930,709.00 |  |
| 21 | Office of Transport-Vehicle Inspection (Area) Office and Inland Waterways | 1,745,000.00 | 750,000.00 | - | - |  |
| 22 | Ministry of Works and Infrastructure | 108,763,293.85 | 87,347,254.77 | 3,950,000,000.00 | 2,790,197,407.73 |  |
| 23 | Ondo State Agency for Road Maintenance and Construction (OSAMCO) | 12,500,000.00 | 9,332,400.00 | 112,500,000.00 | 19,144,822.00 |  |
| 24 | Ondo State Electricity Board(OSEB) | 165,733,661.26 | 34,154,082.75 | 162,500,000.00 | - |  |
| 25 | Ondo State Water Corporation | 160,715,779.62 | 110,823,067.85 | 1,151,040,000.00 | - |  |
| 26 | Ondo State Rural Water Supply and Sanitation Agency (RUWASSA) | 8,216,517.60 | 6,718,003.73 | 76,250,000.00 | 41,141,452.00 |  |
| 27 | Ondo State Development and Property Corporation | 32,695,932.97 | 30,604,894.42 | 78,500,000.00 | - |  |
| 28 | Direct Labour Agency | 2,250,000.00 | 1,050,000.00 | 5,000,000.00 | 7,892,923.25 |  |
| 29 | Ministry of Lands and Housing | 26,932,826.46 | 50,261,204.50 | 250,000,000.00 | 80,953,473.01 |  |
| 30 | Ministry of Physical Planning and Urban Development | 58,017,944.32 | 35,689,329.76 | 35,000,000.00 | 3,532,446.00 |  |
| 31 | Office of Public Utilities | 22,500,000.00 | 2,849,999.99 | 75,000,000.00 | 3,250,000.00 |  |
|  | SUB TOTAL: Infrastructure | 711,453,797.97 | 467,145,315.06 | 5,945,790,000.00 | 2,949,043,232.99 |  |
| A4 | PUBLIC FINANCE SUB SECTOR |  |  |  |  |  |
| 32 | Ondo State Bureau of Statistics | 34,692,700.91 | 13,606,501.69 | 37,500,000.00 | - |  |
| 33 | Board of Internal Revenue | 214,813,371.99 | 135,846,457.28 | 22,500,000.00 | 2,380,075.00 |  |
| 34 | Ministry of Economic Planning and Budget | 192,591,839.53 | 56,229,480.84 | 405,800,000.00 | 3,461,000.00 |  |
| S/N | SECTOR/MDAs/INSTITUTIONS | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |  |
|  |  | THIRD QUARTER ESTIMATES | THIRD QUARTER ACTUAL | THIRD QUARTER ESTIMATES |  | THIRD QUARTER ACTUAL |
| 35 | Budget Office | 5,000,000.00 | 1,800,000.00 | - | - |  |
| 36 | Manpower Development/MEMIS Project Offices | 2,500,000.00 | 975,000.00 | - | - |  |
| 37 | Project and Price Monitoring Unit (PPMU) | 3,750,000.00 | 1,687,500.00 | 21,250,000.00 | 1,959,045.00 |  |
| 38 | State Information Technology Agency (SITA) | 31,514,949.71 | 23,579,903.48 | 32,500,000.00 | 21,258,126.00 |  |
| 39 | State Information Technology Agency (SITA) Area Offices | 2,250,000.00 | 1,350,000.00 | - | - |  |
| 40 | Office of the State Auditor General | 70,410,307.10 | 67,607,509.65 | 2,500,000.00 | - |  |
| 41 | Office of Auditor General for Local Government | 19,407,933.98 | 21,717,785.76 | 2,000,000.00 | 840,000.00 |  |
| 42 | Pools Bettings and Lotteries Board | 875,000.00 | 950,000.00 | - | - |  |
| 43 | Ministry of Finance | 4,246,518,961.75 | 2,019,765,277.73 | 16,200,000.00 | 4,482,500.00 |  |
| 44 | Expenditure Office | 5,000,000.00 | 5,100,000.00 | - | - |  |
| 45 | Debt Management Office | 4,500,000.00 | 3,600,000.00 | 1,250,000.00 | - |  |
| 46 | Office of the Accountant General | 95,711,214.25 | 61,961,476.81 | 165,000,000.00 | 69,085,995.15 |  |
| 47 | Youth Employment and Social Support Operations (YESSO) | 3,000,000.00 | 1,500,000.00 | 20,000,000.00 | - |  |
|  | SUB TOTAL: Public Finance | 4,932,536,279.21 | 2,417,276,893.24 | 726,500,000.00 | 103,466,741.15 |  |
|  | TOTAL ECONOMIC SECTOR | 6,199,992,719.31 | 3,343,720,149.36 | 9,800,986,250.00 | 3,242,299,426.14 |  |
| B | SOCIAL SERVICES SECTOR: |  |  |  |  |  |
| B1 | EDUCATION SUB SECTOR |  |  |  |  |  |
| 48 | Zonal Teaching Service Commission, Owena | 937,500.00 | 750,000.00 | 500,000.00 | - |  |
| 49 | Zonal Teaching Service Commission, Owo | 937,500.00 | 750,000.00 | 500,000.00 | - |  |
| 50 | Ondo State Scholarship Board | 15,769,428.43 | 7,456,323.96 | 130,225,000.00 | - |  |
| 51 | Board of Adult, Technical and Vocational Education | 153,063,591.71 | 104,951,693.63 | 31,250,000.00 | - |  |
| 52 | University Teaching Hospital | - | - | - | - |  |
| 53 | Zonal Teaching Service Commission, Akure | 937,500.00 | 750,000.00 | 500,000.00 | - |  |
| S/N | SECTOR/MDAs/INSTITUTIONS | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |  |
|  |  | THIRD QUARTER ESTIMATES | THIRD QUARTER ACTUAL | THIRD QUARTER ESTIMATES |  | THIRD QUARTER ACTUAL |
| 54 | Zonal Teaching Service Commission, Ikare | 937,500.00 | 750,000.00 | 500,000.00 | - |  |
| 55 | Zonal Teaching Service Commission, Irele | 937,500.00 | 750,000.00 | 500,000.00 | - |  |
| 56 | Zonal Teaching Service Commission, Odigbo | 937,500.00 | 750,000.00 | 500,000.00 | - |  |
| 57 | Zonal Teaching Service Commission, Oka | 937,500.00 | 750,000.00 | 750,000.00 | - |  |
| 58 | Zonal Teaching Service Commission, Okitipupa | 937,500.00 | 750,000.00 | 500,000.00 | - |  |
| 59 | Zonal Teaching Service Commission, Ondo | 937,500.00 | 750,000.00 | 500,000.00 | - |  |
| 60 | Ministry of Education, Science and Technology | 491,605,222.50 | 389,827,000.14 | 378,750,000.00 | 7,500,000.00 |  |
| 61 | Zonal Education Offices | 937,500.00 | 1,350,000.00 | - | - |  |
| 62 | Ondo State Education Endowment Fund Office | 405,000.00 | 600,000.00 | - | - |  |
| 63 | State Universal Basic Education Board (SUBEB) Headquarters | 156,929,541.68 | 78,468,143.42 | 2,443,171,592.00 | 5,600,000.00 |  |
| 64 | State Universal Basic Education Board (Subeb) Zonal Office | 6,047,800.00 | 1,500,000.00 | - |  |  |
| 65 | Mega Schools | 6,120,000.00 | 9,375,000.00 | - | - |  |
| 66 | Ondo State Library Board | 11,297,275.50 | 8,900,071.31 | 17,500,000.00 | - |  |
| 67 | Rufus Giwa polytechnic, Owo | 717,500,000.00 | 1,259,447,384.00 | 25,000,000.00 | - |  |
| 68 | Adekunle Ajasin University, Akungba Akoko | 482,792,421.52 | 595,000,000.00 | 50,000,000.00 | - |  |
| 69 | Ondo State University of Science and Technology, Okitipupa | 194,250,000.00 | 233,000,000.00 | 300,000,000.00 | 10,000,000.00 |  |
| 70 | Teaching Service Commission | 3,725,002,911.89 | 3,730,293,193.31 | 5,000,000.00 | - |  |
|  | Teaching Service Commission (SEC) | - | - | - | - |  |
| 71 | Ondo State University of Medical Sciences | 150,000,000.00 | 180,000,000.00 | 125,000,000.00 | 50,000,000.00 |  |
|  | SUB TOTAL: Education Sub-sector | 6,120,158,193.23 | 6,606,918,809.77 | 3,510,646,592.00 | 73,100,000.00 |  |
| B2 | HEALTH SUB SECTOR |  |  |  |  |  |
| S/N | SECTOR/MDAs/INSTITUTIONS | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |  |
|  |  | THIRD QUARTER ESTIMATES | THIRD QUARTER ACTUAL | THIRD QUARTER ESTIMATES |  | THIRD QUARTER ACTUAL |
| 72 | Ondo State Agency for the Control of Aids (ODSACA) | 2,500,000.00 | 600,000.00 | 37,500,000.00 | 9,283,000.00 |  |
| 73 | Primary Health Care Management Board | 74,518,114.01 | 89,426,213.30 | 899,533,695.75 | - |  |
| 74 | Hospital Management Board | 1,782,936,192.16 | 1,932,455,801.06 | 40,750,000.00 | 35,000,000.00 |  |
| 75 | School of Nursing | 675,000.00 | 525,000.00 | 15,750,000.00 | - |  |
| 76 | School of Midwifery | 675,000.00 | - | 7,500,000.00 | - |  |
| 77 | School of Health Technology | 675,000.00 | 675,000.00 | 2,500,000.00 | 945,000.00 |  |
| 78 | Emergency Medical Services Agency | 18,000,000.00 | 1,875,000.00 | 12,500,000.00 | - |  |
| 79 | Board of Alternative Medicine | 582,075.00 | 300,000.00 | 500,000.00 | - |  |
| 80 | Neuro-Psychiatric Specialist Hospital | 1,690,750.00 | 1,749,000.00 | 1,250,000.00 | - |  |
| 81 | Ministry of Health | 182,058,921.75 | 133,654,315.53 | 828,000,000.00 | 50,778,000.00 |  |
|  | SUB TOTAL: Health Sub-Sector | 2,064,311,052.91 | 2,161,260,329.89 | 1,845,783,695.75 | 96,006,000.00 |  |
| B3 | SOCIAL AND COMMUNITY DEV. SUB SECTOR |  |  |  |  |  |
| 82 | Ondo State Football Development Agency | 182,500,000.00 | 180,000,000.00 | 27,500,000.00 | - |  |
| 83 | Ministry of Youth and Sports Development | 27,815,007.85 | 29,194,519.00 | 25,000,000.00 | - |  |
| 84 | Ministry of Women Affairs and Social Development | 115,130,783.15 | 139,124,881.18 | 11,250,000.00 | - |  |
| 85 | Agency for the Welfare of the Physically Challenged Persons | 6,350,000.00 | 2,250,000.00 | 1,250,000.00 | 996,584.00 |  |
| 86 | Ondo State Sports Council | 71,986,253.46 | 72,185,939.05 | 7,500,000.00 | - |  |
| 87 | Ondo State Football Academy | 20,000,000.00 | - | - | - |  |
| 88 | Ondo State Community and Social Development Agency | 2,150,000.00 | 12,531,203.79 | 147,500,000.00 | - |  |
| 89 | Directorate of Rural and Community Development | 8,500,000.00 | 4,800,000.00 | 405,750,000.00 | 4,980,000.00 |  |
|  | SUB TOTAL: Social and Community Dev. Sub-Sector | 434,432,044.45 | 440,086,543.02 | 625,750,000.00 | 5,976,584.00 |  |
| B4 | Environment and Sewage Management Sub-Sector | - | - | - | - |  |
| S/N | SECTOR/MDAs/INSTITUTIONS | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |  |
|  |  | THIRD QUARTER ESTIMATES | THIRD QUARTER ACTUAL | THIRD QUARTER ESTIMATES |  | THIRD QUARTER ACTUAL |
| 90 | Ondo State Waste Management | 73,339,948.49 | 83,214,275.78 | 15,000,000.00 | 21,287,700.00 |  |
| 91 | Ondo State Waste Management Authority Area Office Ondo | - | 2,850,000.00 | - | - |  |
| 92 | Ministry of Environment | 54,104,444.47 | 45,021,212.86 | 437,500,000.00 | 31,113,855.00 |  |
| 93 | Environmental Task Force | - | - | - | - |  |
|  | SUB TOTAL: Environment and Sewage Management | 127,444,392.96 | 131,085,488.64 | 452,500,000.00 | 52,401,555.00 |  |
|  | TOTAL SOCIAL SERVICES SECTOR: | 8,746,345,683.55 | 9,339,351,171.32 | 6,434,680,287.75 | 227,484,139.00 |  |
| C | LAW AND JUSTICE SECTOR |  |  |  |  |  |
| C1 | Administration of Justice |  |  |  |  |  |
| 94 | ONDO STATE JUDICIARY | 400,665,646.35 | 495,882,734.97 | 295,000,000.00 | 36,910,180.61 |  |
| 95 | ONDO STATE JUDICIAL SERVICE COMMISSION | 24,289,938.16 | 11,250,000.00 | 2,500,000.00 | 5,000,000.00 |  |
| 96 | OFFICE OF HONOURABLE CHIEF JUDGE | 7,500,000.00 | 5,400,000.00 | - | - |  |
| 97 | JUDICIARY DIVISION | 5,000,000.00 | 5,625,000.00 | - | - |  |
| 98 | Mobile Court | - | - | - | - |  |
| 99 | MINISTRY OF JUSTICE | 75,493,232.77 | 86,791,198.33 | 55,500,000.00 | 39,889,190.00 |  |
| 100 | ONDO STATE LAW COMMISSION | 5,853,993.42 | 7,027,034.27 | 10,000,000.00 | 4,819,629.18 |  |
| 101 | CITIZEN'S RIGHT MEDIATION CENTRE/OFFICE OF PUBLIC DEFENDERS | 1,566,000.00 | 1,800,000.00 | - | - |  |
| 102 | High Court | - | - | - | - |  |
| 103 | CUSTOMARY COURT OF APPEAL | 15,750,000.00 | 22,701,000.00 | 1,250,000.00 | 957,000.00 |  |
| 104 | Customary Court of appeal- judicial divisions | 3,500,000.00 | 3,375,000.00 | - | - |  |
| 105 | OFFICE OF THE PRESIDENT OF THE CUSTOMARY COURT OF APPEAL | 5,000,000.00 | 4,725,000.00 | - | - |  |
|  | TOTAL: LAW AND JUSTICE SECTOR | 544,618,810.71 | 644,576,967.57 | 364,250,000.00 | 87,575,999.79 |  |
| D | ADMINISTRATION SECTOR |  |  |  |  |  |
| S/N | SECTOR/MDAs/INSTITUTIONS | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |  |
|  |  | THIRD QUARTER ESTIMATES | THIRD QUARTER ACTUAL | THIRD QUARTER ESTIMATES |  | THIRD QUARTER ACTUAL |
| D1 | General Administration Sub - Sector | - | - | - |  |  |
| 106 | Governor's Office-Government House and Protocol | 723,167,076.01 | 433,997,188.69 | 60,000,000.00 | 50,692,291.00 |  |
| 107 | Deputy Governor's Office | 122,636,542.41 | 101,892,069.62 | 1,037,750,000.00 | - |  |
| 108 | Office of Senior Special Assistants to the Governor | 18,000,000.00 | 24,000,000.00 | - | - |  |
| 109 | Office of the Special Advisers to the Governor | 15,000,000.00 | 1,500,000.00 | - | - |  |
| 110 | SSA on Procurrement | - | 1,500,000.00 | - | - |  |
| 111 | Ondo State Boundary Commission | 4,350,000.00 | 2,767,500.00 | 1,250,000.00 | - |  |
| 112 | Nigeria Security and Civil Defence Corps | 500,000.00 | 464,800.00 | - | - |  |
| 113 | Office of the Head of Service | 12,000,000.00 | 7,800,000.00 | 2,500,000.00 | 837,650.00 |  |
| 114 | Senior Staff Club | 750,000.00 | 700,000.00 | - | - |  |
| 115 | Public Service Training Institute | 7,800,000.00 | 5,041,830.00 | 20,000,000.00 | - |  |
| 116 | Office of Establishments | 131,765,471.17 | 49,011,044.33 | 3,750,000.00 | 759,660.00 |  |
| 117 | Office of the Secretary to State Government (SSG) | 2,376,000.00 | 2,250,000.00 | - | - |  |
| 118 | E-Personel Administration Salary System (e-PASS) Office | 1,387,500.00 | 300,000.00 | - | - |  |
| 119 | General Administration | 68,765,196.12 | 74,967,953.32 | 121,500,000.00 | 106,796,145.86 |  |
| 120 | Political and Economic Affairs Department | 735,949,810.57 | 188,962,573.15 | - | - |  |
| 121 | State Emergency Management Agency (SEMA) | - | - | 17,500,000.00 | - |  |
| 122 | Cabinet and Special Services Department | 30,078,269.47 | 21,067,922.45 | 1,250,000.00 | 3,267,942.00 |  |
| 123 | Liaison Office, Lagos | 34,814,188.71 | 51,747,165.33 | 2,500,000.00 | - |  |
| 124 | Liaison Office, Abuja | 17,205,669.33 | 7,149,821.81 | 2,000,000.00 | - |  |
| 125 | Service Matters Department | 20,750,000.00 | 7,233,150.00 | 1,250,000.00 | - |  |
| 126 | Ministry of Regional Integration and Special Duties | 23,141,011.34 | 10,721,845.92 | 150,000,000.00 | - |  |
| S/N | SECTOR/MDAs/INSTITUTIONS | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |  |
|  |  | THIRD QUARTER ESTIMATES | THIRD QUARTER ACTUAL | THIRD QUARTER ESTIMATES |  | THIRD QUARTER ACTUAL |
| 127 | Fire Services | 1,350,000.00 | - | - | - |  |
| 128 | Public Complaint Commission/Ombudsman | - | - | - | - |  |

| 129 | Ondo State Pensions Transitional Department | 11,560,493.83 | 11,696,879.70 | 55,000,000.00 | - |
| --- | --- | --- | --- | --- | --- |
| 130 | Muslim Welfare Board | 9,875,000.00 | 22,290,203.00 | 6,250,000.00 | - |
| 131 | Christian Welfare Board | 13,900,000.00 | 750,000.00 | 3,750,000.00 | 3,000,000.00 |
| 132 | Civil Service Commission | 32,107,952.77 | 28,384,839.10 | 3,250,000.00 | - |
| 133 | Ondo State Independent Electoral Commission (ODIEC) | 18,662,361.93 | 13,063,226.80 | 502,500,000.00 | 10,000,000.00 |
| 134 | Ondo State Independent Electoral Commission (ODIEC) Area Offices | 500,000.00 | 337,500.00 | - | - |
| 135 | Ministry of Local Government and Chieftaincy Affairs | 45,667,989.26 | 15,405,230.39 | 3,000,000.00 | - |
| 136 | Local Government Service Commission | 1,012,500.00 | 450,000.00 | 3,750,000.00 | - |
| 137 | Inter-Governmental Affairs and Multilateral Relations | 5,262,500.00 | 637,500.00 | 1,395,707,520.75 | 9,730,000.00 |
| 138 | Nigerian Legion | 1,000,000.00 | 840,000.00 | - | - |
| 139 | Consolidated Revenue Fund Charges | 3,125,000,000.00 | 4,103,021,833.73 | - | - |
| 140 | Provision for other Grants and Loans | 832,433,365.68 | 9,999,799.92 | - | - |
| 141 | State Counterpart Fund to Local Government Councils for Capital Projects | - | - | - | - |
| 142 | Government Quarters Management Office | 950,000.00 | 600,000.00 | - | - |
| 143 | State Pension Commission | 11,462,144.13 | 9,720,750.60 | 6,250,000.00 | - |
| 144 | SA on Youth and Student Affairs | - | 1,800,000.00 | - | - |
| 145 | Office of Labour and Union Matters | 4,000,000.00 | 1,999,999.98 | - | - |
|  | SA on Multilateral relations | - |  | - |  |
|  | Deputy Chief of Staff | - |  | - |  |

| S/N | SECTOR/MDAs/INSTITUTIONS | RECURRENT EXPENDITURE |  | CAPITAL EXPENDITURE |  |
| --- | --- | --- | --- | --- | --- |
|  |  | THIRD QUARTER ESTIMATES | THIRD QUARTER ACTUAL | THIRD QUARTER ESTIMATES | THIRD QUARTER ACTUAL |

|  | SUB TOTAL: General Administration | 3,161,192,886.12 | 1,118,550,794.11 | 3,400,707,520.75 | 185,083,688.86 |
| --- | --- | --- | --- | --- | --- |
| D2 | LEGISLATIVE SUB-SECTOR |  |  |  |  |
| 145 | State House of Assembly | 650,298,968.83 | 357,097,625.34 | 123,285,000.00 | 6,789,601.89 |
| 146 | House of Assembly Commission | 29,188,215.94 | 18,446,657.89 | 5,087,250.00 | - |
| 147 | Offices of the Speaker | 24,000,000.00 | 12,600,000.00 | - | - |
| 148 | Office of the deputy speaker | 19,875,000.00 | 10,433,250.00 | - | - |
| 149 | Public Account secretariat | 2,000,000.00 | - | - | - |
|  | SUB TOTAL: General Administration | 725,362,184.77 | 398,577,533.23 | 128,372,250.00 | 6,789,601.89 |
| D3 | INFORMATION SUB-SECTOR |  |  |  |  |
| 150 | Ondo State Radiovision Corporation | 66,005,518.95 | 52,626,460.24 | 55,000,000.00 | - |
| 151 | Ministry of Information and Orientation | 138,889,902.63 | 92,327,989.75 | 25,000,000.00 | 42,768,913.66 |
| 152 | Orange FM | 19,516,165.50 | 16,319,900.61 | 17,000,000.00 | 9,941,750.00 |
| 153 | Government Printing Press | 2,495,000.00 | 450,000.00 | 1,250,000.00 | - |
| 154 | Ondo State Signage Agency | 5,000,000.00 | 600,000.00 | 3,750,000.00 | 1,500,000.00 |
| 155 | Owena Press | 37,500,000.00 | 35,465,600.00 | 1,250,000.00 | - |
|  | SUB TOTAL: Information | 269,406,587.08 | 197,789,950.60 | 103,250,000.00 | 54,210,663.66 |
|  | TOTAL: ADMINISTRATION | 4,155,961,657.96 | 1,714,918,277.94 | 3,632,329,770.75 | 246,083,954.41 |
|  | GRAND TOTAL | 19,646,918,871.52 | 19,145,588,399.92 | 20,232,246,308.50 | 3,803,443,519.34 |